## Sheet1
2023-08-07
|  | Bid Due | 2023-08-09
|  | Project range | $ 1.5M to $ 3M
|  | Projce Duration | 720 days
|  | Liquidated Damages | 2000
HS 696 (M) - Waste System, Parapets and Exterior Masonry
525 East Houston Street, New York, NY 10002
Description | Quantity | Unit Type | Unit Cost | Total | Notes
General Conditions
Project Management | 18 | Months |  | 0 | 720 CCD - Duration of Contract (for Estimating purposes we use 18 months for all field construction)
Supervision | 18 | Months |  | 0
Progress Housekeeping - Laborer (Local 79) | 18 | Months |  | 0
Temporaty Offices | 1 | LS |  | 0
Security Guard Services | 9984 | HRS |  | 0 | Duration x 128 HR/per week for 18 months
Custodian Permits | 2730 | HRS |  | 0 | Duration x 35 HR/week for 18 months
Permits | 1 | LS |  | 0
Mobilization | 1 | LS |  | 0
Final Clean-up | 1 | LS |  | 0
Baseline Schedule | 1 | LS |  | 0
Schedule Update | 18 | Each |  | 0
Submittals/ Shop Drawings | 1 | LS |  | 0
Safety Plans (SSP) | 1 | LS |  | 0
Scaffolding | 0 | SF |  | 0 | N/A
Sidewalk Bridge | 0 | LF |  | 0
Scaffolding Rental | 0 | Month |  | 0
Sidewalk Bridge Rental | 0 | Months |  | 0
Construction Fence atround the perimeter of the jobsite/ Stagin Area | 1 | LS |  | 0
Staging Area | 1 | LS |  | 0
Demobilization | 1 | LS |  | 0
After Hour Variance Permit | 1 | LS |  | 0
Temp Electrical Panels | 0 | Each |  | 0 | Tentative
Containers | 1 | LS |  | 0
Non power toold for to cut mortar and point (SHPO Building) |  |  |  |  | Just for Information
Total |  |  |  | 0
Asbesto Abatement
Pipe/ Pipe Joint Insualtion Removal | 1 | EA |  | 0
Total |  |  |  | 0
Demolition
Demo Sections of wall for new plumbing penetration | 4 | EA |  | 0
Remove Wrought Iron Fnece and Store for Repaint and Repairs (Height 5' 3" or 3') | 125 | LF |  | 0
Remove Exisitng Coping Stone | 145 | LF |  | 0
Remove Exising Hand Rails | 213 | LF |  | 0
Remove Exisitng Face Brick | 1435 | SF |  | 0
Scarify Concrete Landings, Treads and Risers of Staircase | 835 | SF |  | 0
Grind out 1/2" of parpaet structure 2/A083 | 2 | LF |  | 0
Grind out 1" x 1/2" groove for new reglet and flashing 2/A083 | 2 | EA |  | 0
Relocate Exisitng Flood Barrier Storage Rack and the items in the rack | 2 | EA |  | 0
Sawcut and remove floor slab and vinyl flors, Trench for plumbing lines. Excavation per specs 02090 | 240 | SF |  | 0
Remove Existing 8" CMU wall from first floor slab to underside of second floor. | 68 | SF |  | 0
Sawcut and remove floor slab, excavat for new pit, trench for plumbing lines | 17 | SF |  | 0
Remove Exisitng Plaster | 255 | SF |  | 0
Total |  |  |  | 0
Metal
Install Repainted and Repaired Wrought Iron Fnece | 125 | LF |  | 0
Install New Handrails 8/A408 | 200 | LF |  | 0
Furnish and Install Rooftop Metal Fence 2/A406 Various Sizes | 390 | SF |  | 0
New Metal Stair Treads (6' x 11") | 8 | EA |  | 0
New Stair Steel Grating Landing (6'x3') | 1 | EA |  | 0
New Stair C Chanel Stringers | 25 | LF |  | 0
New Stair 1-1/2" Schedule 40 Handrail | 110 | LF |  | 0 | All the metal for the handrail
Total |  |  |  | 0
Masonry
Provide CMU Partition Wall 75% grouted 3/A-404 | 68 | SF |  | 0
Coping Replacement 5/A408 | 126 | LF |  | 0
Peovide new facebrick | 1100 | SF |  | 0
Provide New Vertical Expansion Joint 2/A408 | 40 | LF |  | 0
Replace Stone Band 7/A408 | 20 | LF |  | 0
Total |  |  |  | 0
Roofing
Install Kemper Waterproofing Membrane 4,5,6,7/ A408 | 840 | SF |  | 0
Regled With lead wedge selant | 3 | EA |  | 0
Copper Floashing welded to exisitng pipe | 2 | LF |  | 0
Perforated Aluminium Screen Fasten to parapet wall | 2 | LF |  | 0
Provide pitch pockets at roof penetration | 2 | EA |  | 0
Total |  |  |  | 0
Concrete
Provide Reinforced Concrete Slab (12" thick) with #4 at 6'' O.C | 250 | SF |  | 0
Provide a new pit and a 4'x3' hatch to accomodate new storm outfall trap 5/A404 | 1 | EA |  | 0
12" of Gravel | 12 | SF |  | 0
#5 @ 12" Rebar | 870 | LF |  | 0
#4 Rebar | 180 | LF |  | 0
Concrete Pour | 60 | CF |  | 0
Crysteline Waterproofing the Pit | 70 | SF |  | 0
Total |  |  |  | 0
Paint
All New Piping installed within cafeteria to be painted to match exisiting | 1 | LS
Provide New Plaster Finish Over Existing Brick, Prime and Paint to Match Existing | 260 | SF
Total |  |  |  | 0
Electric
Electirc Subcontractor | 1 | LS |  | 0
Plumbing
Plumbing Subcontractor | 1 | LS |  | 0
Total |  |  |  | 0